## Sheet1
Algo Terminal Testing
S.No. | Bug/Issue/Features Details | Status | Feedback | Other Info | TYPE
1 | History Need to Save in DataBase of Strategy. | IS PENDING |  |  | Features
2 | Leg Name Issue Bug When more the Five Re_Entry Happen. | IS COMPLETE |  |  | defect
3 | Stg Name Issue was random the name got incorrect. | IS COMPLETE |  |  | defect
4 | Add New Details Form for overall strategy in Main Form. | IS PENDING |  |  | Features
5 | In Top Instead of Algo Trade write $" Trader Code {Total Profit}". | IS PENDING |  |  | Features
6 | Add Status in overall strategy main form.(Complete/Started/Runing) . | IS PENDING |  |  | Features
7 | Control The strategy using Start and Stop Command. | IS PENDING |  |  | Features | Stop command is done using ctrl+T.
8 | Collaspe all and Expend all button need to add. | IS PENDING |  |  | Features | Need to check posibility.
9 | Color Need to add if any stg has Error or UnExpected behaviour in stg. Also Need to provide a Command to change the color back to initial stage. | IS PENDING |  |  | Features
10 | Excel need to Add with in Application code for config.ini | IS COMPLETE |  |  | n/a
11 | Unhedge Case Manage | IS PENDING |  |  | Features
12 | Add MIDCPNIFTY | IS COMPLETE |  |  | Features
13 | Check bid>0, Ask>0,VolumeTraded>0 for premium if fail then do not take entry in Leg. | IS PENDING |  |  | Features
14 | if using Trail SL, once SL set to 0 the sl does not work until it move futher. | IN TESTING |  |  | defect
15 | Client get stuck while testing need to anaylize the root cause. (Occurance random.) | IS PENDING |  |  | defect | Not able to find till now.
16 | StopLoss can not be in Negative after math must set it to Zero. | IS PENDING |  |  | defect
17 | Re-Entry of leg rejection got delay after Exit from strategy. | IS COMPLETE |  |  | defect
18 | When Re_Entry is fast the Entry and Exit price not able to update because of LTP. | IS PENDING |  |  | defect
19